## Test Runs
Test Key | Test Summary | Test Type | Test Label(s) | Test Component(s) | Test Priority | Total Parameters | Parameters | Requirements | Test Plan Key | Test Execution Key | FixVersion(s) | Revision | Execution Status | TE assignee | TE planned begin date | TE planned end date | Assignee | Executed by | Test Environment(s) | Started at | Finished at | Elapsed | Elapsed (sec) | Comment | Total Defects | Defects
PSTM-44 | TC011 Test if system user should be able to Search for an existing item | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 07:44:45 | 21/05/2023 07:44:52 | 0:00 | 7 |  | 0
PSTM-49 | TC012 Test if system user should not be able to earch for an inexisting item | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 07:49:12 | 21/05/2023 07:49:27 | 0:00 | 15 |  | 0
PSTM-52 | TC013 Test if user is not able to Search with blank space | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 07:59:37 | 21/05/2023 07:59:44 | 0:00 | 7 |  | 0
PSTM-56 | TC014 Test if user can add products to cart form the product display page | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:02:12 | 21/05/2023 08:02:19 | 0:00 | 7 |  | 0
PSTM-58 | TC015 Test if customer can add the product to cart form the wish list (Favorite) page | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:03:25 | 21/05/2023 08:03:40 | 0:00 | 15 |  | 0
PSTM-60 | TC016 Test if customer can remove a product from shopping cart | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:05:05 | 21/05/2023 08:05:28 | 0:00 | 23 |  | 0
PSTM-63 | TC017 Test if a costumer can be able to provide the delivery details | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:06:25 | 21/05/2023 08:06:34 | 0:00 | 9 |  | 0
PSTM-66 | TC018 Test if a costumer can be able to choose a payment option | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:07:28 | 21/05/2023 08:07:37 | 0:00 | 9 |  | 0
PSTM-69 | TC019 Test if the costumer can be able to place the order | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:08:23 | 21/05/2023 08:08:35 | 0:00 | 12 |  | 0
PSTM-44 | TC011 Test if system user should be able to Search for an existing item | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 07:44:45 | 21/05/2023 07:44:52 | 0:00 | 7 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;0].Comment} | 0
PSTM-49 | TC012 Test if system user should not be able to earch for an inexisting item | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 07:49:12 | 21/05/2023 07:49:27 | 0:00 | 15 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;1].Comment} | 0
PSTM-52 | TC013 Test if user is not able to Search with blank space | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 07:59:37 | 21/05/2023 07:59:44 | 0:00 | 7 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;2].Comment} | 0
PSTM-56 | TC014 Test if user can add products to cart form the product display page | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:02:12 | 21/05/2023 08:02:19 | 0:00 | 7 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;3].Comment} | 0
PSTM-58 | TC015 Test if customer can add the product to cart form the wish list (Favorite) page | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:03:25 | 21/05/2023 08:03:40 | 0:00 | 15 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;4].Comment} | 0
PSTM-60 | TC016 Test if customer can remove a product from shopping cart | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:05:05 | 21/05/2023 08:05:28 | 0:00 | 23 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;5].Comment} | 0
PSTM-63 | TC017 Test if a costumer can be able to provide the delivery details | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:06:25 | 21/05/2023 08:06:34 | 0:00 | 9 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;6].Comment} | 0
PSTM-66 | TC018 Test if a costumer can be able to choose a payment option | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:07:28 | 21/05/2023 08:07:37 | 0:00 | 9 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;7].Comment} | 0
PSTM-69 | TC019 Test if the costumer can be able to place the order | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:08:23 | 21/05/2023 08:08:35 | 0:00 | 12 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;8].Comment} | 0
PSTM-3 | TC001 Test if sign up lik is shown | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 04:48:36 | 20/05/2023 04:49:04 | 0:00 | 28 |  | 0
PSTM-9 | TC 002 Test if user see the registration form | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:01:55 | 20/05/2023 05:02:29 | 0:01 | 34 |  | 0
PSTM-11 | TC003 Test if user can activate the account | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:12:18 | 20/05/2023 05:12:54 | 0:01 | 36 |  | 0
PSTM-14 | TC004 Test if user can log-in with valid credentials | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:45:08 | 20/05/2023 05:46:16 | 0:01 | 68 |  | 0
PSTM-19 | TC006 Test if user can log in with invalid credentials (e-mail adress) | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:56:21 | 20/05/2023 05:56:35 | 0:00 | 14 |  | 0
PSTM-17 | TC005 Test if user can log-in with invalid credentials (invalid password) | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:50:30 | 20/05/2023 05:50:49 | 0:00 | 19 |  | 0
PSTM-22 | TC007 Test if user can sign in with Facebook credentials | Manual |  |  | Medium | 0 |  | PSTM-21 | PSTM-37 | PSTM-38 |  |  | FAILED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 06:36:15 | 20/05/2023 06:36:28 | 0:00 | 13 | An error message will appear | 2 | PSTM-42
PSTM-26 | TC008 Test if System user can reset password | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 06:03:53 | 20/05/2023 06:04:24 | 0:01 | 31 |  | 0
PSTM-29 | TC009 Test if the password meets the security requirements | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | FAILED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 06:08:37 | 20/05/2023 07:22:18 | 1:14 | 4421 | I changed it with "1234" and it worked. No error message will appear | 2 | PSTM-41
PSTM-32 | TC010 Test login with differed passwords | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 06:19:09 | 20/05/2023 06:19:23 | 0:00 | 14 |  | 0
PSTM-3 | TC001 Test if sign up lik is shown | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 04:48:36 | 20/05/2023 04:49:04 | 0:00 | 28 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;0].Comment} | 0
PSTM-9 | TC 002 Test if user see the registration form | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:01:55 | 20/05/2023 05:02:29 | 0:01 | 34 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;1].Comment} | 0
PSTM-11 | TC003 Test if user can activate the account | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:12:18 | 20/05/2023 05:12:54 | 0:01 | 36 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;2].Comment} | 0
PSTM-14 | TC004 Test if user can log-in with valid credentials | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:45:08 | 20/05/2023 05:46:16 | 0:01 | 68 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;3].Comment} | 0
PSTM-19 | TC006 Test if user can log in with invalid credentials (e-mail adress) | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:56:21 | 20/05/2023 05:56:35 | 0:00 | 14 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;4].Comment} | 0
PSTM-17 | TC005 Test if user can log-in with invalid credentials (invalid password) | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:50:30 | 20/05/2023 05:50:49 | 0:00 | 19 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;5].Comment} | 0
PSTM-22 | TC007 Test if user can sign in with Facebook credentials | Manual |  |  | Medium | 0 |  | PSTM-21 | PSTM-37 | PSTM-38 |  |  | FAILED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 06:36:15 | 20/05/2023 06:36:28 | 0:00 | 13 | An error message will appear | 2 | PSTM-42
PSTM-26 | TC008 Test if System user can reset password | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 06:03:53 | 20/05/2023 06:04:24 | 0:01 | 31 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;7].Comment} | 0
PSTM-29 | TC009 Test if the password meets the security requirements | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | FAILED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 06:08:37 | 20/05/2023 07:22:18 | 1:14 | 4421 | I changed it with "1234" and it worked. No error message will appear | 2 | PSTM-41
PSTM-32 | TC010 Test login with differed passwords | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 06:19:09 | 20/05/2023 06:19:23 | 0:00 | 14 | ${wiki:TestExecutions[variableName=j;0].TestRuns[variableName=n;9].Comment} | 0

## Test Runs including iterations
Test Key | Test Summary | Test Type | Test Label(s) | Test Components(s) | Test Priority | Total Parameters | Parameters | Requirements | Test Plan Key | Test Execution Key | FixVersion(s) | Revision | Execution status | TE assignee | TE planned begin date | TE planned end date | Assignee | Executed by | Test Environment(s) | Started at | Finished at | Elapsed | Elapsed (sec) | Comment | Total Defects | Defects
PSTM-44 | TC011 Test if system user should be able to Search for an existing item | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 07:44:45 | 21/05/2023 07:44:52 | 0:00 | 7 |  | 0
PSTM-49 | TC012 Test if system user should not be able to earch for an inexisting item | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 07:49:12 | 21/05/2023 07:49:27 | 0:00 | 15 |  | 0
PSTM-52 | TC013 Test if user is not able to Search with blank space | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 07:59:37 | 21/05/2023 07:59:44 | 0:00 | 7 |  | 0
PSTM-56 | TC014 Test if user can add products to cart form the product display page | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:02:12 | 21/05/2023 08:02:19 | 0:00 | 7 |  | 0
PSTM-58 | TC015 Test if customer can add the product to cart form the wish list (Favorite) page | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:03:25 | 21/05/2023 08:03:40 | 0:00 | 15 |  | 0
PSTM-60 | TC016 Test if customer can remove a product from shopping cart | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:05:05 | 21/05/2023 08:05:28 | 0:00 | 23 |  | 0
PSTM-63 | TC017 Test if a costumer can be able to provide the delivery details | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:06:25 | 21/05/2023 08:06:34 | 0:00 | 9 |  | 0
PSTM-66 | TC018 Test if a costumer can be able to choose a payment option | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:07:28 | 21/05/2023 08:07:37 | 0:00 | 9 |  | 0
PSTM-69 | TC019 Test if the costumer can be able to place the order | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 21/05/2023 08:08:23 | 21/05/2023 08:08:35 | 0:00 | 12 |  | 0
PSTM-44 | TC011 Test if system user should be able to Search for an existing item | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 07:44:45 | 21/05/2023 07:44:52 | 0:00 | 7 |  | 0
PSTM-49 | TC012 Test if system user should not be able to earch for an inexisting item | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 07:49:12 | 21/05/2023 07:49:27 | 0:00 | 15 |  | 0
PSTM-52 | TC013 Test if user is not able to Search with blank space | Manual |  |  | Medium | 0 |  | PSTM-43 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 07:59:37 | 21/05/2023 07:59:44 | 0:00 | 7 |  | 0
PSTM-56 | TC014 Test if user can add products to cart form the product display page | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:02:12 | 21/05/2023 08:02:19 | 0:00 | 7 |  | 0
PSTM-58 | TC015 Test if customer can add the product to cart form the wish list (Favorite) page | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:03:25 | 21/05/2023 08:03:40 | 0:00 | 15 |  | 0
PSTM-60 | TC016 Test if customer can remove a product from shopping cart | Manual |  |  | Medium | 0 |  | PSTM-55 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:05:05 | 21/05/2023 08:05:28 | 0:00 | 23 |  | 0
PSTM-63 | TC017 Test if a costumer can be able to provide the delivery details | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:06:25 | 21/05/2023 08:06:34 | 0:00 | 9 |  | 0
PSTM-66 | TC018 Test if a costumer can be able to choose a payment option | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:07:28 | 21/05/2023 08:07:37 | 0:00 | 9 |  | 0
PSTM-69 | TC019 Test if the costumer can be able to place the order | Manual |  |  | Medium | 0 |  | PSTM-62 | PSTM-48 | PSTM-72 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 21/05/2023 08:08:23 | 21/05/2023 08:08:35 | 0:00 | 12 |  | 0
PSTM-3 | TC001 Test if sign up lik is shown | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 04:48:36 | 20/05/2023 04:49:04 | 0:00 | 28 |  | 0
PSTM-9 | TC 002 Test if user see the registration form | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:01:55 | 20/05/2023 05:02:29 | 0:01 | 34 |  | 0
PSTM-11 | TC003 Test if user can activate the account | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:12:18 | 20/05/2023 05:12:54 | 0:01 | 36 |  | 0
PSTM-14 | TC004 Test if user can log-in with valid credentials | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:45:08 | 20/05/2023 05:46:16 | 0:01 | 68 |  | 0
PSTM-19 | TC006 Test if user can log in with invalid credentials (e-mail adress) | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:56:21 | 20/05/2023 05:56:35 | 0:00 | 14 |  | 0
PSTM-17 | TC005 Test if user can log-in with invalid credentials (invalid password) | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 05:50:30 | 20/05/2023 05:50:49 | 0:00 | 19 |  | 0
PSTM-22 | TC007 Test if user can sign in with Facebook credentials | Manual |  |  | Medium | 0 |  | PSTM-21 | PSTM-37 | PSTM-38 |  |  | FAILED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 06:36:15 | 20/05/2023 06:36:28 | 0:00 | 13 | An error message will appear | 2 | PSTM-42
PSTM-26 | TC008 Test if System user can reset password | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 06:03:53 | 20/05/2023 06:04:24 | 0:01 | 31 |  | 0
PSTM-29 | TC009 Test if the password meets the security requirements | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | FAILED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 06:08:37 | 20/05/2023 07:22:18 | 1:14 | 4421 | I changed it with "1234" and it worked. No error message will appear | 2 | PSTM-41
PSTM-32 | TC010 Test login with differed passwords | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu | test | 20/05/2023 06:19:09 | 20/05/2023 06:19:23 | 0:00 | 14 |  | 0
PSTM-3 | TC001 Test if sign up lik is shown | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 04:48:36 | 20/05/2023 04:49:04 | 0:00 | 28 |  | 0
PSTM-9 | TC 002 Test if user see the registration form | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:01:55 | 20/05/2023 05:02:29 | 0:01 | 34 |  | 0
PSTM-11 | TC003 Test if user can activate the account | Manual |  |  | Medium | 0 |  | PSTM-2 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:12:18 | 20/05/2023 05:12:54 | 0:01 | 36 |  | 0
PSTM-14 | TC004 Test if user can log-in with valid credentials | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:45:08 | 20/05/2023 05:46:16 | 0:01 | 68 |  | 0
PSTM-19 | TC006 Test if user can log in with invalid credentials (e-mail adress) | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:56:21 | 20/05/2023 05:56:35 | 0:00 | 14 |  | 0
PSTM-17 | TC005 Test if user can log-in with invalid credentials (invalid password) | Manual |  |  | Medium | 0 |  | PSTM-13 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 05:50:30 | 20/05/2023 05:50:49 | 0:00 | 19 |  | 0
PSTM-22 | TC007 Test if user can sign in with Facebook credentials | Manual |  |  | Medium | 0 |  | PSTM-21 | PSTM-37 | PSTM-38 |  |  | FAILED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 06:36:15 | 20/05/2023 06:36:28 | 0:00 | 13 | An error message will appear | 2 | PSTM-42
PSTM-26 | TC008 Test if System user can reset password | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 06:03:53 | 20/05/2023 06:04:24 | 0:01 | 31 |  | 0
PSTM-29 | TC009 Test if the password meets the security requirements | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | FAILED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 06:08:37 | 20/05/2023 07:22:18 | 1:14 | 4421 | I changed it with "1234" and it worked. No error message will appear | 2 | PSTM-41
PSTM-32 | TC010 Test login with differed passwords | Manual |  |  | Medium | 0 |  | PSTM-25 | PSTM-37 | PSTM-38 |  |  | PASSED | Sabin Marcu |  |  | Sabin Marcu | Sabin Marcu |  | 20/05/2023 06:19:09 | 20/05/2023 06:19:23 | 0:00 | 14 |  | 0

## Input Issues
Key | Issue Type | Summary | Priority | Component(s) | Status | Assignee
PSTM-72 | Test Execution | Test Execution for Test Plan PSTM-48 (Sprint 2) | Medium |  | Done | Sabin Marcu
PSTM-71 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-70 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-69 | Xray Test | TC019 Test if the costumer can be able to place the order | Medium |  | Done | Sabin Marcu
PSTM-68 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-67 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-66 | Xray Test | TC018 Test if a costumer can be able to choose a payment option | Medium |  | Done | Sabin Marcu
PSTM-65 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-64 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-63 | Xray Test | TC017 Test if a costumer can be able to provide the delivery details | Medium |  | Done | Sabin Marcu
PSTM-62 | Story | Checkout Functionality | Medium |  | Done | Sabin Marcu
PSTM-61 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-60 | Xray Test | TC016 Test if customer can remove a product from shopping cart | Medium |  | Done | Sabin Marcu
PSTM-59 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-58 | Xray Test | TC015 Test if customer can add the product to cart form the wish list (Favorite) page | Medium |  | Done | Sabin Marcu
PSTM-57 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-56 | Xray Test | TC014 Test if user can add products to cart form the product display page | Medium |  | Done | Sabin Marcu
PSTM-55 | Story | Add to cart Functionality | Medium |  | Done | Sabin Marcu
PSTM-54 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-53 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-52 | Xray Test | TC013 Test if user is not able to Search with blank space | Medium |  | Done | Sabin Marcu
PSTM-51 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-50 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-49 | Xray Test | TC012 Test if system user should not be able to earch for an inexisting item | Medium |  | Done | Sabin Marcu
PSTM-48 | Test Plan | Test plan for sprint 2 | Medium |  | Done | Sabin Marcu
PSTM-47 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-46 | Test Set | TS002 | Medium |  | Done | Sabin Marcu
PSTM-45 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-44 | Xray Test | TC011 Test if system user should be able to Search for an existing item | Medium |  | Done | Sabin Marcu
PSTM-43 | Story | Search Bar functionality | Medium |  | Done | Sabin Marcu
PSTM-42 | Bug | User is not able to connect with Facebook | Medium |  | Done | Sabin Marcu
PSTM-41 | Bug | The password don’t meet the minimum password strength. | Medium |  | Done | Sabin Marcu
PSTM-38 | Test Execution | Test Execution for Test Plan PSTM-37 (Sprint 1) | Medium |  | Done | Sabin Marcu
PSTM-37 | Test Plan | Test plan for Sprint 1 | Medium |  | Done | Sabin Marcu
PSTM-34 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-33 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-32 | Xray Test | TC010 Test login with differed passwords | Medium |  | Done | Sabin Marcu
PSTM-31 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-30 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-29 | Xray Test | TC009 Test if the password meets the security requirements | Medium |  | Done | Sabin Marcu
PSTM-28 | Precondition | User should be logged in | Medium |  | Done | Sabin Marcu
PSTM-27 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-26 | Xray Test | TC008 Test if System user can reset password | Medium |  | Done | Sabin Marcu
PSTM-25 | Story | Reset Password Functionality | Medium |  | Done | Sabin Marcu
PSTM-24 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-23 | Precondition | User must have a Facebook account | Medium |  | Done | Sabin Marcu
PSTM-22 | Xray Test | TC007 Test if user can sign in with Facebook credentials | Medium |  | Done | Sabin Marcu
PSTM-21 | Story | Sign in with Facebook | Medium |  | Done | Sabin Marcu
PSTM-20 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-19 | Xray Test | TC006 Test if user can log in with invalid credentials (e-mail adress) | Medium |  | Done | Sabin Marcu
PSTM-18 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-17 | Xray Test | TC005 Test if user can log-in with invalid credentials (invalid password) | Medium |  | Done | Sabin Marcu
PSTM-16 | Precondition | Login credential for an existing account | Medium |  | Done | Sabin Marcu
PSTM-15 | Precondition | Website https://starshiners.ro/ should be up | Medium |  | Done | Sabin Marcu
PSTM-14 | Xray Test | TC004 Test if user can log-in with valid credentials | Medium |  | Done | Sabin Marcu
PSTM-13 | Story | Log-in Functionality | Medium |  | Done | Sabin Marcu
PSTM-12 | Precondition | website should be up | Medium |  | Done | Sabin Marcu
PSTM-11 | Xray Test | TC003 Test if user can activate the account | Medium |  | Done | Sabin Marcu
PSTM-10 | Precondition | The website should be up | Medium |  | Done | Sabin Marcu
PSTM-9 | Xray Test | TC 002 Test if user see the registration form | Medium |  | Done | Sabin Marcu
PSTM-5 | Test Set | TS001 website test set | Medium |  | Done
PSTM-4 | Precondition | Website should be uo | Medium |  | Done | Sabin Marcu
PSTM-3 | Xray Test | TC001 Test if sign up lik is shown | Medium |  | Done | Sabin Marcu
PSTM-2 | Story | Sign up Functionality | Medium |  | Done | Sabin Marcu